## Estimation Sheet_
Chevron | 112.5833 | **** Efforts per site except admin setup |  |  | 14.0729 | 0.58637
[5 empty] | Time in Min | 10 | 15 | 15 | 0 | 20 | 120 | 0 | 180 | 60 | 180 | 45 | 180 | 20 | 10 | 0
| Total Efforts Estimation | 112.5833 |  |  | Factors | 0.16667 | 0.25 | 0.25 | 0 | 0.33333 | 2 | 0 | 3 | 1 | 3 | 0.75 | 3 | 0.33333 | 0.16667 | 0
Row Labels | Sum of Sum of Total Bends, Teex, Reducers | Sum of Sum of Total Equipmets | Sum of Sum of Total Valves | Total Line Numbers | Total Line Segments | Efforts for Volume Creation | Efforts for Centreline Creation | Creation of Line List | Efforts for 3D Markups | Efforts for 3d modelling (Piping with flange, bends, Flanges, Tees) | Efforts for Equipment Development | Admin Setup & Proposal | Plot Plan | Equipment Layouts | P&ID | PFD | Piping Isometrics | Bulk MTO | EquipmentTagging | Nozzle Orientations | Subtotal
01 - CON001 - Boast | 30 | 2 | 15 | 5 | 50 | 97 | 50 | 50 | 50 | 80 | 2 | 60 | 5 | 2 | 2 | 1 | 5 | 5 | 2 | 2
Total Hours | C | D | E | A | F | 16.1667 | 12.5 | 12.5 | 0 | 26.6667 | 4 | 0 | 15 | 2 | 6 | 0.75 | 15 | 1.6667 | 0.33333 | 0 | 112.5833
[6 empty] | Pipe Modelling |  |  |  |  | Equipment Modelling | Admin Set up | Deliverables
| Efforts for 1st Site including efforts of 1 time project set-up | Hours | [17 empty] | Average Hrs per site | 112.5833
| P&ID’s – assume 3x per site | 67.4062
| PFD(s) - assume 1x per site | 21.4688
| General arrangement - assume 1x per site | 29.9688
| Inspection Isometrics - assume 3x per site | 73.4062
| Tagging of equipment – assume 33 per site | 5.5
197.75
h
Quantity Caps
Platform | Particular | Unit Qty | Total Qty per site
| Total P&ID per site | 3
Chevron | Total Line No per P&ID | 8 | 24
| Bends, Teex, Reducers per P&ID | 20 | 60
| Total Line segments per line | 28 | 84
| Total Equipments per P&ID | 11 | 33
| Total number of Valves per P&ID | 20 | 60
3D Modelling efforts
Site Name | SCOPE | Total Line Count | Total Number of expected P&ID | Bends, Teex, Reducers per P&ID | Total Equipments per P&ID | Total number of Valves per P&ID | Total Line segments per line
01 - CON001 - Boast | In scope | 5 | 3 | 30 | 2 | 15 | 50
|  | A | B | C | D | E | F
02 - CON001 - Boast Receiver | In scope | 4 | 2 | 24 | 2 | 12 | 40
03 - CON002 - Roth FED | In scope | 4 | 2 | 24 | 2 | 12 | 40
04 - CON004 - Orr | In scope | 5 | 3 | 30 | 2 | 15 | 50
05 - CON004 - Orr Receiver | In scope | 5 | 3 | 30 | 2 | 15 | 50
06 - CON008 - Troudt | In scope | 5 | 3 | 30 | 2 | 15 | 50
07 - CON394 - Grand Mesa | In scope | 12 | 6 | 72 | 5 | 36 | 120
08 - CON398 - Harvester | In scope | 10 | 5 | 60 | 4 | 30 | 100
09 - CON420 - Leftner Troudt Re | In scope | 7 | 4 | 42 | 3 | 21 | 70
10 - CON444 - Roth Launcher | In scope | 6 | 3 | 36 | 3 | 18 | 60
11 - CON417 Laramie | In scope | 7 | 4 | 42 | 3 | 21 | 70
12 - Onion | (blank)

## Master File
Site Name | POIS__TITLE__EN | Line ID | SCOPE | POI_TYPES__ID | Site Name | SCOPE | Count of Line ID
01 - CON001 - Boast | South oil LACT reject line | <p>Captured on LACT P&amp;ID, out of scope.</p> | Out of scope | 3529 | 01 - CON001 - Boast | In scope | 5
01 - CON001 - Boast | PW LACT Inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | Out of scope | 3529 |  | Out of scope | 5
01 - CON001 - Boast | Oil LACT discharge header buried pipe | <p>Continues to Bost Launcher</p> | In scope | 3529 | 02 - CON001 - Boast Receiver | In scope | 4
01 - CON001 - Boast | North oil LACT Inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | Out of scope | 3529 | 03 - CON002 - Roth FED | In scope | 4
01 - CON001 - Boast | North oil LACT discharge | <p>In scope&nbsp;continues to buried pipe.</p> | In scope | 3529 |  | Out of scope | 3
01 - CON001 - Boast | PW LACT discharge | <p>Continue to buried pipe</p> | In scope | 3529 | 04 - CON004 - Orr | In scope | 5
01 - CON001 - Boast | North Oil LACT reject line | <p>Captured on LACT P&amp;ID, out of scope.</p> | Out of scope | 3529 |  | Out of scope | 5
01 - CON001 - Boast | South oil LACT discharge | <p>In scope continues to buried pipe</p> | In scope | 3529 | 05 - CON004 - Orr Receiver | In scope | 5
01 - CON001 - Boast | PW LACT discharge buried pipe | <p>Continues to Bost Launcher</p> | In scope | 3529 | 06 - CON008 - Troudt | In scope | 5
01 - CON001 - Boast | South oil LACT inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | Out of scope | 3529 |  | Out of scope | 2
02 - CON001 - Boast Receiver | Oil from Bost LACT | <p>through COG2200</p> | In scope | 3550 | 07 - CON394 - Grand Mesa | In scope | 12
02 - CON001 - Boast Receiver | PW from Bost LACT | <p>through route COG2113</p> | In scope | 3550 | 08 - CON398 - Harvester | In scope | 10
02 - CON001 - Boast Receiver | Oil pipeline to Roth | <p>Continue to route COG2201</p> | In scope | 3550 | 09 - CON420 - Leftner Troudt Re | In scope | 7
02 - CON001 - Boast Receiver | PW pipeline to Roth | <p>To CON444 Roth Crude Launcher through route COG2113</p> | In scope | 3550 | 10 - CON444 - Roth Launcher | In scope | 6
03 - CON002 - Roth FED | Oil LACT discharge | <p>Continue to buried pipe</p> | In scope | 3569 | 11 - CON417 Laramie | In scope | 7
03 - CON002 - Roth FED | PW LACT discharge buried pipe | <p>Continue to CON444 Roth Crude Launcher through route COG2116</p> | In scope | 3569 | 12 - Onion | (blank)
03 - CON002 - Roth FED | PW LACT inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | Out of scope | 3569
03 - CON002 - Roth FED | PW LACT discharge | <p>continue to buried pipe</p> | In scope | 3569
03 - CON002 - Roth FED | Oil LACT reject line | <p>covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3569
03 - CON002 - Roth FED | Oil LACT discharge buried pipe | <p>Continue to CON444 Roth Crude Launcher through route COG2202</p> | In scope | 3569
03 - CON002 - Roth FED | Oil LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3569
04 - CON004 - Orr | East oil LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3490
04 - CON004 - Orr | From west oil LACT |  | In scope | 3490
04 - CON004 - Orr | West Oil LACT reject line | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3490
04 - CON004 - Orr | Oil LACT header buried pipe | <p>To Orr launcher through COG2205</p> | In scope | 3490
04 - CON004 - Orr | East oil LACT discharge | <p> to header</p> | In scope | 3490
04 - CON004 - Orr | East oil LACT reject line | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3490
04 - CON004 - Orr | PW discharge to Orr launcher | <p>through COG2112</p> | In scope | 3490
04 - CON004 - Orr | West oil LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3490
04 - CON004 - Orr | PW LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3490
04 - CON004 - Orr | West oil LACT discharge | <p>to header </p> | In scope | 3490
04 - CON004 - Orr | PW LACT discharge | <p>LACT P&amp;ID should cover to SDV</p> | In scope | 3490
05 - CON004 - Orr Receiver | Oil from CON444 Roth Crude Launcher | <p>through route COG2203</p> | In scope | 3510
05 - CON004 - Orr Receiver | PW from Orr and Roth Crude Launcher | <p>Through COG2112 and COG2113</p> | In scope | 3510
05 - CON004 - Orr Receiver | Oil to Empire Trunk line | <p>through COL2201</p> | In scope | 3510
05 - CON004 - Orr Receiver | Oil from CON004 Orr | <p>from COG2205</p> | In scope | 3510
05 - CON004 - Orr Receiver | PW to Monarch TL | <p>through COG2100</p> | In scope | 3510
06 - CON008 - Troudt | Oil LACT Inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3429
06 - CON008 - Troudt | PW LACT outlet |  | In scope | 3429
06 - CON008 - Troudt | Oil discharge header deadleg | <p>in scope</p> | In scope | 3429
06 - CON008 - Troudt | Oil to pipeline | <p>Continue to CON420 Leftner/Troudt receiver, through COG2212</p> | In scope | 3429
06 - CON008 - Troudt | PW LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3429
06 - CON008 - Troudt | PW to pipeline | <p>to CON420 Leftner/Troudt Receivers, through route COG2107</p> | In scope | 3429
06 - CON008 - Troudt | Oil LACT discharge | <p>to launcher</p> | In scope | 3429
06 - CON008 - Troudt | Oil LACT reject line | <p>Covered on LACT P&amp;ID, out of scope.</p> | Out of scope | 3429
07 - CON394 - Grand Mesa | Oil from Grand Mesa Launcher pad | <p>From the middle pig trap pad, through onsite underground piping. </p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil metering station to Grand Mesa launcher | <p>To launcher to the west of the pad through underground piping onsite.</p> | In scope | 3389
07 - CON394 - Grand Mesa | oil drain to sump |  | In scope | 3389
07 - CON394 - Grand Mesa | Oil from Lucerne | <p>through route </p> | In scope | 3389
07 - CON394 - Grand Mesa | oil drain to sump |  | In scope | 3389
07 - CON394 - Grand Mesa | Oil new project tie-in | <p>Unknown continuation.</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil continues to NGL skid | <p>To south metering pad through onsite underground pipng</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil inlet from Grand Mesa Launcher | <p>From Greely Cresent field, through route COG2215</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil continue to Lucerne | <p>through route COL3301</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil new project tie-in | <p>Unknown continuation.</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil new project tie-in | <p>unkown continuation.</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil from GC field | <p>from route COL2201</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil from Grand Mesa Skid | <p>From north metering skid through onsite underground piping.</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil to Grand Mesa north metering skid |  | In scope | 3389
07 - CON394 - Grand Mesa | Oil new project tie-in | <p>unkown continuation</p> | In scope | 3389
07 - CON394 - Grand Mesa | Oil demarcation to NGL |  | In scope | 3389
08 - CON398 - Harvester | Oil from CON012 Harvester | <p>through route COG2611</p> | In scope | 3409
08 - CON398 - Harvester | PW from NW valve loop | <p>through underground piping onsite.</p> | In scope | 3409
08 - CON398 - Harvester | Oil to pipeline | <p>To route COG2608</p> | In scope | 3409
08 - CON398 - Harvester | PW to pipeline | <p>continue to route COG2105</p> | In scope | 3409
08 - CON398 - Harvester | Oil from NW receiver. | <p>through underground piping on site</p> | In scope | 3409
08 - CON398 - Harvester | Oil from CON453 Thorton LACT and launcher | <p>through route COG2608</p> | In scope | 3409
08 - CON398 - Harvester | Oil to pipeline | <p>To route COG2608</p> | In scope | 3409
08 - CON398 - Harvester | Oil to valve loop | <p>through onsite underground piping.</p> | In scope | 3409
08 - CON398 - Harvester | PW continue to SE valve loop | <p>through underground piping onsite.</p> | In scope | 3409
08 - CON398 - Harvester | PW from CON012 Harvester | <p>through route COG2104</p> | In scope | 3409
09 - CON420 - Leftner Troudt Re | PW from CON008 Troudt | <p>through COG2107</p> | In scope | 3470
09 - CON420 - Leftner Troudt Re | Oil from CON008 Troudt | <p>through route COG2212</p> | In scope | 3470
09 - CON420 - Leftner Troudt Re | PW from pipeline | <p>from route COG2106</p> | In scope | 3470
09 - CON420 - Leftner Troudt Re | PW to pipeline | <p>to route COG2106</p> | In scope | 3470
09 - CON420 - Leftner Troudt Re | Oil to pipeline | <p>To Empire trunk line, through COL2201</p> | In scope | 3470
09 - CON420 - Leftner Troudt Re | PW to pipeline | <p>to route COG2100</p> | In scope | 3470
09 - CON420 - Leftner Troudt Re | Oil from pipeline | <p>From CON010&nbsp;LEFFLER-DONN through route COG2211</p> | In scope | 3470
10 - CON444 - Roth Launcher | PW to CON004 Orr | <p>through route COG2203</p> | In scope | 3589
10 - CON444 - Roth Launcher | PW from CON001 Bost | <p>from route COG2201</p> | In scope | 3589
10 - CON444 - Roth Launcher | Oil from north Kiyoshi launcher |  | In scope | 3589
10 - CON444 - Roth Launcher | PW from CON002 Roth FED | <p>through COG2116</p> | In scope | 3589
10 - CON444 - Roth Launcher | Oil to pipeline | <p>continues to CON001 Bost through route COG2201</p> | In scope | 3589
10 - CON444 - Roth Launcher | Oil from CON002 Roth FED | <p>through COG2202</p> | In scope | 3589
10 - CON444 - Roth Launcher | Oil to pipeline | <p>To CON004 Orr through route COG2203</p> | In scope | 3589
10 - CON444 - Roth Launcher | Oil to south Bost receiver |  | In scope | 3589
11 - CON417 Laramie | Oil continues to Mountainview and goes to Milton | <p>through route COL2801</p> | In scope | 3623
11 - CON417 Laramie | Oil inlet from Kiyoshi launcher | <p>throguh route COL2202</p> | In scope | 3623
11 - CON417 Laramie | Oil from west of the pad | <p>through underground piping onsite</p> | In scope | 3623
11 - CON417 Laramie | Oil to east of the pad | <p>through underground piping onsite.</p> | In scope | 3623
11 - CON417 Laramie | Oil to Energy Transfer | <p>through route COL2200</p> | In scope | 3623
11 - CON417 Laramie | Oil drain going to sump | <p>through underground piping onsite.</p> | In scope | 3623
11 - CON417 Laramie | oil drain to sump | <p>through underground piping onsite</p> | In scope | 3623
12 - Onion

## 01 - CON001 - Boast
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
31.2834 | 49.0026 | 2.0471 | 0 | 0.024151 | -0.958 | 0.28574 | #103386306189456 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:57:47+0000 | South oil LACT reject line | <p>Captured on LACT P&amp;ID, out of scope.</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
16.4008 | 30.4865 | 2.2416 | 0 | -0.25707 | -0.029381 | 0.96595 | #758481293016570 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:56:53+0000 | PW LACT Inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
10.3981 | 16.7103 | 2.237 | 0 | 0.13534 | 0.61937 | 0.77335 | #1328017609639811 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:18:48+0000 | Oil LACT discharge header buried pipe | <p>Continues to Bost Launcher</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
30.614 | 55.1348 | 2.0834 | 0 | -0.81936 | -0.15968 | 0.55059 | #2307535783452314 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:57:12+0000 | North oil LACT Inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
32.0894 | 61.5016 | 2.1277 | 0 | -0.77482 | 0.62037 | 0.12168 | #2514369191389581 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:16:34+0000 | North oil LACT discharge | <p>In scope&nbsp;continues to buried pipe.</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
11.5358 | 30.193 | 2.2637 | 0 | -0.17433 | 0.87605 | 0.44961 | #2515789682827160 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:20:46+0000 | PW LACT discharge | <p>Continue to buried pipe</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
31.1579 | 61.4894 | 1.8812 | 0 | -0.058695 | 0.042399 | 0.99738 | #2600460269792108 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:57:33+0000 | North Oil LACT reject line | <p>Captured on LACT P&amp;ID, out of scope.</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
31.9021 | 49.0407 | 2.0667 | 0 | -0.69732 | -0.69524 | 0.17432 | #3492250701262929 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:15:23+0000 | South oil LACT discharge | <p>In scope continues to buried pipe</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
6.0491 | 30.3253 | 2.0125 | 0 | -0.37911 | -0.34696 | 0.85784 | #3671632392833200 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:21:46+0000 | PW LACT discharge buried pipe | <p>Continues to Bost Launcher</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous
30.3588 | 43.2309 | 2.065 | 0 | -0.27895 | 0.66241 | 0.69527 | #3848468105099363 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:57:24+0000 | South oil LACT inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | 3529 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1240 | Verschiedene | Miscellaneous

## 02 - CON001 - Boast Receiver
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
31.844521067490128 | 19.257122815170348 | 1.4974117595632515 | 0 | -0.21689 | -0.97143 | 0.096358 | #155744983681110 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:41:27+0000 | Oil from Bost LACT | <p>through COG2200</p> | 3550 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1247 | Verschiedene | Miscellaneous
33.242013257472514 | 25.748217096281866 | 1.6293325717378149 | 0 | -0.37174 | 0.4059115606297023 | 0.8348922629293284 | #2568702436374770 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:42:14+0000 | PW from Bost LACT | <p>through route COG2113</p> | 3550 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1247 | Verschiedene | Miscellaneous
30.087092483557985 | 22.054898749369464 | 1.577224466836624 | 0 | 0.046887 | 0.6205146724974252 | 0.78279 | #2666083973079116 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:24:32+0000 | Oil pipeline to Roth | <p>Continue to route COG2201</p> | 3550 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1247 | Verschiedene | Miscellaneous
25.14944676012809 | 25.966942555828915 | 1.6045404452418406 | 0 | -0.42258 | 0.41000228472008104 | 0.8082836889171822 | #3027054311849638 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:10:36+0000 | PW pipeline to Roth | <p>To CON444 Roth Crude Launcher through route COG2113</p> | 3550 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1247 | Verschiedene | Miscellaneous

## 03 - CON002 - Roth FED
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
20.1293 | 20.315 | 1.7867 | 0 | -0.33171 | -0.57484 | 0.74802 | #525442741160238 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:29:42+0000 | Oil LACT discharge | <p>Continue to buried pipe</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous
31.9631 | 27.7041 | 1.3426 | 0 | -0.79073 | -0.12671 | 0.59891 | #977611294112994 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:45:14+0000 | PW LACT discharge buried pipe | <p>Continue to CON444 Roth Crude Launcher through route COG2116</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous
32.0901 | 37.7086 | 1.7147 | 0 | -0.032836 | -0.73893 | 0.67298 | #1909017661373585 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:58:43+0000 | PW LACT inlet | <p>Captured on LACT P&amp;ID, out of scope.</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous
32.0983 | 33.4245 | 1.8105 | 0 | -0.39924 | 0.58195 | 0.70848 | #2916884911045501 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:36:45+0000 | PW LACT discharge | <p>continue to buried pipe</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous
20.0499 | 20.9417 | 1.7999 | 0 | 0.14471 | -0.6018 | 0.78543 | #3086026467250509 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:58:32+0000 | Oil LACT reject line | <p>covered on LACT P&amp;ID, out of scope.</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous
35.6199 | 23.924 | 1.5236 | 0 | -0.080592 | -0.57325 | 0.81541 | #3433830333957545 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T17:34:28+0000 | Oil LACT discharge buried pipe | <p>Continue to CON444 Roth Crude Launcher through route COG2202</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous
14.3377 | 22.1791 | 1.7243 | 0 | -0.069128 | -0.036768 | 0.99693 | #4461598441380233 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T19:58:18+0000 | Oil LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3569 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1254 | Verschiedene | Miscellaneous

## 04 - CON004 - Orr
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
15.1318 | 21.9893 | 2.4614 | 0 | -0.3038 | -0.018243 | 0.95256 | #438953742638559 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:20:53+0000 | East oil LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
21.0026 | 21.6614 | 1.5928 | 0 | -0.051007 | 0.026654 | 0.99834 | #744234787508304 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:24:37+0000 | From west oil LACT |  | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
3.7378 | 22.3405 | 2.397 | 0 | -0.84182 | -0.49391 | 0.21769 | #1727963702102716 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:19:15+0000 | West Oil LACT reject line | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
21.7227 | 20.5784 | 1.5469 | 0 | -0.046839 | 0.76833 | 0.63834 | #2340282219944430 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:24:07+0000 | Oil LACT header buried pipe | <p>To Orr launcher through COG2205</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
19.6076 | 20.6251 | 2.6219 | 0 | -0.10268 | 0.64882 | 0.75398 | #2384291068041251 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:22:57+0000 | East oil LACT discharge | <p> to header</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
14.0799 | 22.0439 | 2.345 | 0 | -0.2898 | -0.15142 | 0.94503 | #2429642266309346 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:21:07+0000 | East oil LACT reject line | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
24.2644 | 30.95 | 1.5918 | 0 | -0.84446 | -0.40208 | 0.35387 | #2489860344788227 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:27:16+0000 | PW discharge to Orr launcher | <p>through COG2112</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
2.611 | 22.2028 | 2.4502 | 0 | -0.85811 | -0.081007 | 0.50704 | #3606886183509480 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:19:39+0000 | West oil LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
25.1646 | 33.9319 | 2.642 | 0 | -0.011315 | 0.60333 | 0.79741 | #3848526644289781 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:25:38+0000 | PW LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
-2.028 | 20.6738 | 2.5509 | 0 | 0.91039 | 0.21653 | 0.35256 | #4162956127891331 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:20:09+0000 | West oil LACT discharge | <p>to header </p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous
24.2797 | 29.7686 | 2.4286 | 0 | 0.49994 | -0.83978 | 0.21174 | #4315734661757723 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:27:49+0000 | PW LACT discharge | <p>LACT P&amp;ID should cover to SDV</p> | 3490 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1226 | Verschiedene | Miscellaneous

## 05 - CON004 - Orr Receiver
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
32.4713 | 33.0837 | 1.6168 | 0 | -0.076508 | 0.19273 | 0.97826 | #482912027513296 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:31:38+0000 | Oil from CON444 Roth Crude Launcher | <p>through route COG2203</p> | 3510 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1233 | Verschiedene | Miscellaneous
38.2593 | 26.0658 | 1.4773 | 0 | 0.56888 | 0.80013 | 0.19018 | #1071554723336439 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:36:55+0000 | PW from Orr and Roth Crude Launcher | <p>Through COG2112 and COG2113</p> | 3510 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1233 | Verschiedene | Miscellaneous
32.7355 | 20.7464 | 1.5942 | 0 | -0.12624 | 0.52263 | 0.84316 | #1294203122654045 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:33:28+0000 | Oil to Empire Trunk line | <p>through COL2201</p> | 3510 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1233 | Verschiedene | Miscellaneous
30.9839 | 32.3329 | 2.1096 | 0 | -0.14173 | 0.23517 | 0.96157 | #3733556919621434 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:28:44+0000 | Oil from CON004 Orr | <p>from COG2205</p> | 3510 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1233 | Verschiedene | Miscellaneous
38.2767 | 30.8051 | 1.5341 | 0 | 0.76541 | -0.64041 | 0.063428 | #4071804577830846 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:38:23+0000 | PW to Monarch TL | <p>through COG2100</p> | 3510 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1233 | Verschiedene | Miscellaneous

## 06 - CON008 - Troudt
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
31.658 | 45.5959 | 1.9137 | 0 | -0.90316 | -0.22076 | 0.36818 | #318881236355113 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:43:26+0000 | Oil LACT Inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
22.758 | 62.6837 | 2.0862 | 0 | -0.61546 | 0.17055 | 0.7695 | #595737854507304 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:50:37+0000 | PW LACT outlet |  | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
50.0802 | 46.3907 | 1.7919 | 0 | -0.7931 | -0.077771 | 0.60411 | #1069284878621585 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:48:17+0000 | Oil discharge header deadleg | <p>in scope</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
53.8517 | 43.1934 | 1.6257 | 0 | -0.36732 | 0.75426 | 0.54421 | #1178118822399897 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:49:41+0000 | Oil to pipeline | <p>Continue to CON420 Leftner/Troudt receiver, through COG2212</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
22.4544 | 58.2118 | 1.9582 | 0 | -0.27153 | 0.62258 | 0.73394 | #1355205008952306 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:54:47+0000 | PW LACT inlet | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
31.8279 | 71.2295 | 2.0699 | 0 | 0.14367 | -0.67504 | 0.72366 | #2042899435999682 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:54:07+0000 | PW to pipeline | <p>to CON420 Leftner/Troudt Receivers, through route COG2107</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
37.9409 | 44.3839 | 2.2541 | 0 | -0.85744 | -0.18597 | 0.47981 | #2637363042136047 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:44:53+0000 | Oil LACT discharge | <p>to launcher</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous
37.7247 | 44.7872 | 1.9941 | 0 | -0.74288 | -0.27544 | 0.61014 | #3949511492732911 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:43:49+0000 | Oil LACT reject line | <p>Covered on LACT P&amp;ID, out of scope.</p> | 3429 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1205 | Verschiedene | Miscellaneous

## 07 - CON394 - Grand Mesa
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
19.7908 | 25.612 | 1.6439 | 0 | -0.19294 | -0.71787 | 0.66891 | #7555140247173 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:25:33+0000 | Oil from Grand Mesa Launcher pad | <p>From the middle pig trap pad, through onsite underground piping. </p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
34.1436 | 39.9559 | 1.4532 | 0 | -0.15948 | -0.86936 | 0.46774 | #306775226919871 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:20:20+0000 | Oil metering station to Grand Mesa launcher | <p>To launcher to the west of the pad through underground piping onsite.</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
19.678 | 37.7854 | 1.3992 | 0 | -0.067859 | -0.15359 | 0.9858 | #352815671209488 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T21:45:13+0000 | oil drain to sump |  | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
-3.1755 | -18.4388 | 1.2214 | 0 | -0.43641 | -0.45062 | 0.77878 | #405982717520289 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T21:29:09+0000 | Oil from Lucerne | <p>through route </p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
24.4068 | 26.7542 | 1.3596 | 0 | -0.044454 | -0.96697 | 0.251 | #1301649923349856 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:15:05+0000 | oil drain to sump |  | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
2.7964 | -17.3754 | 1.3035 | 0 | -0.033647 | -0.78185 | 0.62256 | #2022166117265973 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:19:16+0000 | Oil new project tie-in | <p>Unknown continuation.</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
-4.6993 | -10.6428 | 1.315 | 0 | -0.0027159 | -0.0024993 | 0.99999 | #2048373367787028 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:21:26+0000 | Oil continues to NGL skid | <p>To south metering pad through onsite underground pipng</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
17.7716 | 40.3313 | 1.5361 | 0 | -0.29618 | 0.94949 | 0.10367 | #2085988643804460 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:05:10+0000 | Oil inlet from Grand Mesa Launcher | <p>From Greely Cresent field, through route COG2215</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
-6.1121 | -19.4179 | 1.3593 | 0 | -0.27647 | -0.20711 | 0.93844 | #2519826606667171 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:22:43+0000 | Oil continue to Lucerne | <p>through route COL3301</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
-4.5757 | -17.0311 | 1.3618 | 0 | -0.012871 | -0.5455 | 0.83801 | #2723849914441695 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:24:08+0000 | Oil new project tie-in | <p>Unknown continuation.</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
1.7248 | -21.0467 | 1.313 | 0 | 0.34028 | -0.9378 | 0.068908 | #3376515428532435 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:18:35+0000 | Oil new project tie-in | <p>unkown continuation.</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
0.28997 | -17.8853 | 1.3361 | 0 | -0.43879 | -0.78095 | 0.44449 | #3575244181028957 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:18:15+0000 | Oil from GC field | <p>from route COL2201</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
-7.952 | -12.0626 | 1.3275 | 0 | -0.012815 | 0.80265 | 0.59631 | #3667884088925733 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:22:18+0000 | Oil from Grand Mesa Skid | <p>From north metering skid through onsite underground piping.</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
3.2019 | -15.5594 | 1.3334 | 0 | 0.027026 | 0.78535 | 0.61846 | #3694744784917334 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:16:57+0000 | Oil to Grand Mesa north metering skid |  | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
-7.7276 | -18.3296 | 1.3982 | 0 | -0.0084445 | -0.61128 | 0.79137 | #3829175591809123 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:23:41+0000 | Oil new project tie-in | <p>unkown continuation</p> | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous
33.337 | 28.2795 | 2.698 | 0 | 0.0083693 | -0.62011 | 0.78447 | #3882861396382029 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:12:45+0000 | Oil demarcation to NGL |  | 3389 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1190 | Verschiedene | Miscellaneous

## 08 - CON398 - Harvester
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
48.544 | 39.2601 | 1.5888 | 0 | -0.89748 | -0.1506 | 0.41454 | #8626066372206 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:37:52+0000 | Oil from CON012 Harvester | <p>through route COG2611</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
50.6363 | 30.5466 | 1.4429 | 0 | -0.15825 | 0.66535 | 0.72957 | #992892011908057 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:29:39+0000 | PW from NW valve loop | <p>through underground piping onsite.</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
59.1585 | 26.4772 | 1.5702 | 0 | 0.0016976 | 0.037012 | 0.99931 | #2290213724891926 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:44:06+0000 | Oil to pipeline | <p>To route COG2608</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
55.8866 | 30.3081 | 1.4911 | 0 | 0.0036748 | -0.6702 | 0.74218 | #2600370121458469 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:18:03+0000 | PW to pipeline | <p>continue to route COG2105</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
59.0725 | 28.5414 | 1.4217 | 0 | 0.037499 | 0.81648 | 0.57615 | #2741949428371459 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:30:26+0000 | Oil from NW receiver. | <p>through underground piping on site</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
70.2666 | 35.2524 | 1.2429 | 0 | -0.15275 | 0.17928 | 0.97187 | #3058866499066283 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:31:48+0000 | Oil from CON453 Thorton LACT and launcher | <p>through route COG2608</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
71.8947 | 26.6808 | 1.4112 | 0 | -0.039235 | 0.46212 | 0.88595 | #3590163856176238 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:28:09+0000 | Oil to pipeline | <p>To route COG2608</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
51.637 | 37.3135 | 1.5417 | 0 | 0.016684 | -0.066548 | 0.99764 | #3637102329760032 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:43:21+0000 | Oil to valve loop | <p>through onsite underground piping.</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
49.7813 | 34.8437 | 1.6509 | 0 | -0.05128 | -0.22732 | 0.97247 | #4100596642956485 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-12T00:29:52+0000 | PW continue to SE valve loop | <p>through underground piping onsite.</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous
44.9872 | 34.7582 | 1.7909 | 0 | -0.16274 | 0.77442 | 0.61138 | #4199478482110221 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:15:08+0000 | PW from CON012 Harvester | <p>through route COG2104</p> | 3409 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1198 | Verschiedene | Miscellaneous

## 09 - CON420 - Leftner Troudt Re
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
33.9357 | 57.4859 | 1.7039 | 0 | -0.33133 | 0.30664 | 0.8923 | #1762898557785631 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:03:31+0000 | PW from CON008 Troudt | <p>through COG2107</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous
26.5429 | 46.9149 | 1.5348 | 0 | -0.39582 | 0.30073 | 0.86769 | #2260022670107073 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:57:09+0000 | Oil from CON008 Troudt | <p>through route COG2212</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous
37.3949 | 35.2043 | 1.8312 | 0 | 0.36134 | -0.92932 | 0.076112 | #2302576685445369 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:08:22+0000 | PW from pipeline | <p>from route COG2106</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous
31.7076 | 52.6995 | 1.7978 | 0 | -0.91961 | -0.39208 | 0.024466 | #2427065918524211 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:09:06+0000 | PW to pipeline | <p>to route COG2106</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous
29.5286 | 35.9255 | 1.4529 | 0 | -0.098599 | -0.88393 | 0.45711 | #2869791324178616 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:09:42+0000 | Oil to pipeline | <p>To Empire trunk line, through COL2201</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous
37.4862 | 31.3418 | 1.6196 | 0 | -0.044552 | -0.9172 | 0.39594 | #3278044451390966 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:08:44+0000 | PW to pipeline | <p>to route COG2100</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous
31.71 | 47.2179 | 1.6598 | 0 | -0.61315 | 0.71276 | 0.34063 | #4393128698869515 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T21:10:15+0000 | Oil from pipeline | <p>From CON010&nbsp;LEFFLER-DONN through route COG2211</p> | 3470 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1219 | Verschiedene | Miscellaneous

## 10 - CON444 - Roth Launcher
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
17.035 | 36.0881 | 1.4814 | 0 | -0.22455 | 0.2039 | 0.95289 | #1297860735937111 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:13:36+0000 | PW to CON004 Orr | <p>through route COG2203</p> | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
18.1878 | 28.0217 | 1.4045 | 0 | -0.22397 | 0.25235 | 0.94136 | #1759279052315399 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:12:55+0000 | PW from CON001 Bost | <p>from route COG2201</p> | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
17.8414 | 17.849 | 1.5929 | 0 | -0.97181 | 0.14006 | 0.18967 | #2446033753814194 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:01:20+0000 | Oil from north Kiyoshi launcher |  | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
18.5688 | 30.0757 | 1.47 | 0 | -0.28747 | 0.31599 | 0.90416 | #2990101532136449 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:40:11+0000 | PW from CON002 Roth FED | <p>through COG2116</p> | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
20.4725 | 15.9061 | 1.7016 | 0 | 0.046987 | 0.072447 | 0.99626 | #3060707445317361 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:04:56+0000 | Oil to pipeline | <p>continues to CON001 Bost through route COG2201</p> | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
12.8328 | 34.051 | 1.3844 | 0 | -0.26115 | -0.09888 | 0.96022 | #3071353495868699 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:39:34+0000 | Oil from CON002 Roth FED | <p>through COG2202</p> | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
14.3217 | 34.2599 | 1.3852 | 0 | -0.13551 | 0.13803 | 0.98111 | #3794001171617473 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:03:24+0000 | Oil to pipeline | <p>To CON004 Orr through route COG2203</p> | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous
10.1898 | 30.2294 | 1.2176 | 0 | 0.29568 | -0.50107 | 0.81333 | #4425794962438318 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-08T20:04:08+0000 | Oil to south Bost receiver |  | 3589 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1261 | Verschiedene | Miscellaneous

## 11 - CON417 Laramie
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POIS__TITLE__EN | POIS__DESCRIPTION__EN | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN
63.3446 | 24.5017 | 1.5982 | 0 | -0.026256 | -0.93225 | 0.36087 | #39538835780413 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:56:04+0000 | Oil continues to Mountainview and goes to Milton | <p>through route COL2801</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous
42.3625 | 29.8503 | 1.7038 | 0 | 0.045905 | 0.71502 | 0.69759 | #849815008391408 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:44:45+0000 | Oil inlet from Kiyoshi launcher | <p>throguh route COL2202</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous
64.9884 | 23.0312 | 1.4838 | 0 | 0.058347 | -0.95502 | 0.29075 | #915381242164634 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:50:13+0000 | Oil from west of the pad | <p>through underground piping onsite</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous
39.8826 | 24.0132 | 1.5757 | 0 | 0.0083592 | -0.1537 | 0.98808 | #2564599700212768 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:46:03+0000 | Oil to east of the pad | <p>through underground piping onsite.</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous
67.9709 | 28.1481 | 1.4932 | 0 | -0.041138 | 0.70273 | 0.71027 | #3865547619163128 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:53:08+0000 | Oil to Energy Transfer | <p>through route COL2200</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous
40.543 | 25.4338 | 1.6094 | 0 | -0.037779 | -0.23902 | 0.97028 | #3931242631693850 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:55:05+0000 | Oil drain going to sump | <p>through underground piping onsite.</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous
59.9229 | 22.9572 | 1.5149 | 0 | -0.15838 | -0.95153 | 0.26364 | #4473653402851243 | TRUE | 0.5 |  |  | NAVVIS:Site | 2023-12-11T16:57:16+0000 | oil drain to sump | <p>through underground piping onsite</p> | 3623 | img/poi_navvis/generic_poi.png |  |  | Allgemein | Generic | 1270 | Verschiedene | Miscellaneous

## 12 - Onion
POIS__X | POIS__Y | POIS__Z | POIS__ORIENTATION_X | POIS__ORIENTATION_Y | POIS__ORIENTATION_Z | POIS__ORIENTATION_W | POIS__ID | POIS__VISIBILITY_CHECK | POIS__IMPORTANCE | POIS__CUSTOM_DATA | POIS__ICON | POIS__COORDINATE_SYSTEM | POIS__UPDATED_DATE | POI_TYPES__ID | POI_TYPES__ICON | POI_TYPES__VISIBILITY_ZOOM_MAX | POI_TYPES__VISIBILITY_ZOOM_MIN | POI_TYPES__NAME__DE | POI_TYPES__NAME__EN | POI_TYPE_GROUPS__ID | POI_TYPE_GROUPS__NAME__DE | POI_TYPE_GROUPS__NAME__EN