## Estimation Sheet_
Chevron | 12168.6373 | **** Efforts per site except admin setup |  |  | 1521.0797 |  | 63.3783
[5 empty] | Time in Min |  | 5 | 4 | 0 | 0 | 480 | 180 |  | 0 | 0 |  |  |  | 5 |  | 15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
| Total Efforts Estimation | 12168.6373 |  |  | Factors |  | 0.083333 | 0.066667 | 0 | 0 | 8 | 3 |  | 0 | 0 |  |  |  | 0.083333 |  | 0.25 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
Reference Site | Sum of Sum of Total Bends, Teex, Reducers | Sum of Total Equipmets | Sum of Total Valves | Total Line Numbers | Total Line Segments | Total Estimated Instruments | Efforts for Volume Creation | Efforts for Centreline Creation | Creation of Line List | Efforts for 3D Markups | Efforts for 3d modelling (Piping with flange, bends, Flanges, Tees, Primary Supports) | Efforts for Equipment Development | Admin Setup & Proposal | Plot Plan | Equipment Layouts | Total Number of Decks | Approx Area per Deck Sq Meter | Complex Factor | Structural Modelling | Structural Modelling Man Months | Instrumentation Modelling | HVAC runs Modelling | P&ID Mark up | PFD | Piping Isometrics | Bulk MTO | EquipmentTagging | Nozzle Orientations | Subtotal
LDT_MRJN_162_169, 174_175 | 180 | 11 | 108 | 36 | 324 | 288 | 51 |  |  |  | 96 | 33 | 120 | 0 | 0 | 8 | 218.4 | 0.8 | 116.48 | 14.56 | 72 | 17.472 | 0 | 0 | 0 | 0 | 0 | 0 | 454.952
LDT_MRJN_224_229, 250 | 155 | 10 | 93 | 31 | 279 | 248 |  |  |  |  | 82.6667 | 30 |  | 0 | 0 | 8 | 703 | 0.8 | 374.9333 | 46.8667 | 62 | 56.24 | 0 | 0 | 0 | 0 | 0 | 0 | 605.84
LDT_MRJN_CGI_TP | 145 | 9 | 87 | 29 | 261 | 232 |  |  |  |  | 77.3333 | 27 |  | 0 | 0 | 8 | 891 | 0.8 | 475.2 | 59.4 | 58 | 71.28 | 0 | 0 | 0 | 0 | 0 | 0 | 708.8133
LDT_MRJN_TP-2A | 715 | 43 | 429 | 143 | 1287 | 1144 |  |  |  |  | 381.3333 | 129 |  | 0 | 0 | 9 | 2652 | 0.8 | 1591.2 | 198.9 | 286 | 238.68 | 0 | 0 | 0 | 0 | 0 | 0 | 2626.2133
LDT_MRJN_TP-4 | 775 | 47 | 465 | 155 | 1395 | 1240 |  |  |  |  | 413.3333 | 141 |  | 0 | 0 | 10 | 1075 | 0.8 | 716.6667 | 89.5833 | 310 | 107.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1688.5
Total Hours | 155 | 10 | 93 | 31 | 279 | [5 empty] | 1050.6667 | 360 | 120 | 0 | 0 |  |  |  | 3274.48 |  | 788 | 491.172 | 0 | 0 | 0 | 0 | 0 | 0 | 6084.3187
* Included in 3D modelling
14.56
| Total Circuits | 200 | Total ISO | 600 | [14 empty] | 0.5824
| Scale factor | 9
| Total line numbers | 1800
[8 empty] | No of Instruments per line = | 8
Site | SCOPE | Total Line Count above 1" | Total Number of expected P&ID for Updation | Bends, Teex, Reducers | Total Equipments |  | Total number of Valves | Total Line segments | Total Instruments
LDT_MRJN_162_169, 174_175 | In scope | 36 | 7.2 | 180 | 11 |  | 108 | 324 | 288
LDT_MRJN_224_229, 250 | In scope | 31 | 6.2 | 155 | 10 |  | 93 | 279 | 248
LDT_MRJN_CGI_TP | In scope | 29 | 5.8 | 145 | 9 |  | 87 | 261 | 232
LDT_MRJN_TP-2A | In scope | 143 | 28.6 | 715 | 43 |  | 429 | 1287 | 1144 |  | 480
LDT_MRJN_TP-4 | In scope | 155 | 31 | 775 | 47 |  | 465 | 1395 | 1240 |  | 160
8
18
240
[9 empty] | 5 |  | 4320
[11 empty] | 72 | hrs
[11 empty] | 9 | days

## Summary
Sr. No. | Site | Admin Setup | Piping | Equipment | Instrumentation | Structural | HVAC runs | Total
1 | LDT_MRJN_162_169, 174_175 | 120 | 96 | 33 | 72 | 116.48 | 17.472 | 454.952
2 | LDT_MRJN_176/185 | 120 | 96 | 33 | 72 | 116.48 | 17.472 | 454.952
3 | LDT_MRJN_224_229, 250 | 0 | 82.6667 | 30 | 62 | 374.9333 | 56.24 | 605.84
4 | LDT_MRJN_CGI_TP | 0 | 77.3333 | 27 | 58 | 475.2 | 71.28 | 708.8133
5 | LDT_MRJN_TP-2A | 0 | 381.3333 | 129 | 286 | 1591.2 | 238.68 | 2626.2133
6 | LDT_MRJN_TP-4 | 0 | 413.3333 | 141 | 310 | 716.6667 | 107.5 | 1688.5
6539.2707
Sr. No. | Site | Total
1 | LDT_MRJN_162_169, 174_175 | 505
2 | LDT_MRJN_176/185 | 500
3 | LDT_MRJN_224_229, 250 | 606
4 | LDT_MRJN_CGI_TP | 809